## Untitled
===== WORKSHEET 1: Deliverables Registry =====
Value Physics Research Repository - Master Deliverables Registry
Alethekanon Research Institute ¦ Division 2: Societal Economics & Value Physics ¦ Directory ID: 1ido8K-WwFst-DLzvOuyMB3uNKXPkPAyi ¦ Revision 2026-08-28
Doc ID | Document Title | Formal Category / Role | Theoretical & Empirical Scope | Lifecycle Status | NotebookLM Sync | Google Drive Direct Link
VPE-01 | Formal Paper 6: Value Physics & The Universal Price Tensor | Master Theoretical Treatise | UPE, 3-layer cost (Pe+Pb+Pm), P^7 vector, Lorentz coercion, 56-cell matrices (5 sectors), Leontief-Value tensor, Theorem 5 | Remediated & Verified (Master Draft) | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1PYHxIgClDslPH-sOiNEL5nJtPMPAh9Mfm6yk5bt1Lc4/edit
VPE-02 | Technical Whitepaper: The Tri-Fold Cryptographic Ledger | Cryptographic Protocol Whitepaper | PoD consensus state machine, Book 1/2/3 accounting, 1,000-run Monte Carlo testing | Complete / Validated | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1biBhmIb114Tdb1DkxrqCnxXwngSgnVAjl0ztmcFMBYo/edit
VPE-03 | Econometric Paper: Stock-Flow Consistent Micro-Economy Modeling | Econometric SFC Empirical Treatise | 156-week SFC matrix for NSW broadacre farming, calibrated to ABARES/ABS/RBA/ACCC/AEMO | Complete / Empirical Master | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1vMrZ-UfWr9uv3Uw_nO17yuh5XAbxiVweDIcsINFbMO8/edit
VPE-04 | Research Report: Multi-Commodity Cohesive Village Simulation | Dynamic Multi-Sector Simulation | 600-citizen village across 5 sectors under 3-year compound crises | Complete / Modeled | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1H3LS1DBxUY6crJl6S887MwwNcNmhg3-oWkmg3JKY0rU/edit
VPE-05 | The Cardinal Value Matrix: WEST, EAST, BEST, WORST | Foundational Conceptual Treatise | 4-quadrant token geometry, Need/Want dynamics, Reciprocal Closure Law | Foundational Treatise | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1dgnWZVDQHgKs_35bncktB-L2hxp_hnNrszlO09zgx4c/edit
VPE-06 | The 7-Plane Token Spectrum Architecture | Foundational Currency Architecture | Multi-spectral currency vector, planar action profiles, Plane Misidentification Errors | Foundational Treatise | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1awluVDkDagymqiFV-WbYhehXp8kstoYIHbdcGf8V4Xo/edit
VPE-07 | The Grand Translation to Modern Economic Theory | Cross-Disciplinary Theoretical Suite | Bridges to Neoclassical, Sraffian, Bioeconomic, Post-Keynesian SFC and Austrian schools | Foundational Treatise | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1xqXYmXssgFAHKhSb-3oG2-AwOpNa4nrpnoBEMDi8ywA/edit
VPE-08 | The Bread of Life: Isomorphic Information Treatise | Isomorphic Process Treatise | 8-stage bread lifecycle mapped to Information Theory, Actualism, TS_0 invariant | Foundational Treatise | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1xCq6cmQFgz7NnmYpWwr0fTILNaAHbVQkqGhorsP6eow/edit
VPE-09 | Achilles-Setup-Check: Relational Spacetime & Coordinates | Spacetime Foundations | Zeno resolution, continuous worldlines, self-normalised traversal coordinates | Foundational Theory | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1fwgrHfZJqpy0X_lUEuDABnJgD6WEiL5v9FNx4SCqWEg/edit
VPE-10 | Research Paper: The Economics and Value Physics of Bread | Empirical Case Study | Multi-tier price audit and 5-channel interest rate cost-push transmission | Complete / Empirical Research | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1f4cQwN2Rba5cteU-iWsFCA8MMcOSWRa0IxDDk3x5kM4/edit
VPE-11 | Research Treatise: Cohesive Village Simulation (7 Guilds) | Meso-Scale Simulation Treatise | 600-citizen village across 7 guilds, Tri-Fold Ledger, 104-week audit | Complete / Treatise | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1hm6KOBGml4Sry-kHgoHrrFwC2j542zzah--azRmkUJw/edit
VPE-12 | On the Irreducibility & Necessity of the 7 Interrogative Planes | Foundational Preprint | Zenodo preprint: 42D simplex minimal volume, TEF 126+n nodes, P vs NP collapse. OUTSIDE PRIMARY DIRECTORY. | Preprint / Foundational | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1aJdkY0SAAldN38JT4av1Pw-_Vh3fts0SYkfWl3pqg6s/edit
VPE-13 | Alethekanon Master Organizational Charter | Institutional Governance | Institute charter, Division 1/2 hierarchy, multi-agent triad profiles. OUTSIDE PRIMARY DIRECTORY. | Governance Charter | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1kPFbMJ-1gpD-nh_I6d2hdOpvJ4u9q-VlX9NU2pSDSe0/edit
VPE-14 | Executive Summary & Research Index | Overview & Navigation | Summary of bread metrics, WEST tokens, cross-document navigation | Index / Overview | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1_bek34ggppNV4aYNzjWNhc80eCmEpa0vcjSD98b_23s/edit
VPE-15 | Value Physics Master Excel Ledger | Single Canonical Spreadsheet | Registry, change log, 56-cell verification record, audit tracker, roadmap | Active Canonical Spreadsheet | n/a (this workbook) | (this workbook)
VPE-16 | Orthodox Linker Treatise | Cross-Disciplinary Linker | Mappings to Sraffian Standard Commodities, Godley-Lavoie SFC, Landauer limits. OUTSIDE PRIMARY DIRECTORY. | Formalized & Published | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1-IE4Re1X0WKkWYzW65ZDL_dWW6q4Js4ubipfjcUbwG8/edit
VPE-17 | PREF Companion Treatise: Value Physics & Macro Resolution | Macroeconomic Operating System | Macro architecture integrating UPE, Cardinal Tokens, P_H, Foundational Dividend. OUTSIDE PRIMARY DIRECTORY. | Complete / Framework | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1TH6sMQXLh8ZClsq1JuXMZbEjj5sDggOlXwe1AxPNlxI/edit
VPE-18 | Statutory Model Charter & Sovereign Credit Union Bylaws | Institutional Legal Framework | Model bylaws implementing Theorem 5 (0% usury) and the Tri-Fold Ledger (ARI-VPE-STAT-2026-01) | Complete / Model Bylaws | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1ADVAgqsAh9HjAMeVfLUN3sdqvGd8rUuYrGOc9OjYCc4/edit
VPE-19 | Executive Policy Brief: Agricultural Debt & Supermarket Margins | Sovereign Policy Brief | Submission for Parliamentary/ACCC inquiries on rate-hike cost-push inflation and duopoly caps (ARI-VPE-POL-2026-01) | Complete / Policy Brief | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/15QH8ylkKQBi1PdRC5MgvMjg7L_Nt5pXiPg3ZTGxB87c/edit
VPE-20 | Value Physics Explained: A Plain-English Beginner's Guide | Educational & Public Resource | Plain-English translation of UPE, 3-layer cost, WEST tokens, DQ, Cohesive Village | Complete / Educational Guide | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1yf97wHNNe4HMiA8-GM_tc_Ke3I3GX_hb7H5sB5yKsmI/edit
VPE-21 | The Physics of Economic Value: Academic Journal Manuscript | Unified Academic Treatise | Manuscript for Ecological Economics / JEDC (ARI-VPE-JRNL-2026-01). BLOCKED ON OPEN-02 AND OPEN-04. | Complete / Awaiting Submission Package | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/1Fspsc-AjkvWMmfycQ5P19Jktt14k8hI7OrpDOR1CfmY/edit
VPE-22 | Multi-Village Regional Network Simulation: Decentralized Mutual Credit, Asymmetric Climate Resilience, and Inter-Sovereign Trade Tensor Clearing | Regional Network Protocol | ARI-VPE-SIM-2026-02. 156wk, 10 Warrumbungle-Orana nodes; 6,500 citizens, 70 enterprises; 30wk drought (wks 40-70) at 50% yield loss; diesel $2.40/L; debt to $147.04M; +8.79M Rn; 42.0M WEST reserves | Complete / Simulation Treatise | Synchronized (unverified 2026-08-28) | https://docs.google.com/document/d/15ozakw1icWoyH6Lpy8DCUjF8rXhQLfUPFGGfaJT9Y-g/edit
VPE-23 | Project Management Master Log | Master PM Document | Repository architecture, corpus health audit, evidence standard, verification log, roadmap, open items register | Active Master PM Document | Not synchronized | https://docs.google.com/document/d/16nTfXEjhBeU3zIS0b_B0bJO6y_2gQ-XaIP4DCxalLKs/edit
VPE-24 | Multi-Village Regional Network Simulation: Decentralized Mutual Credit, Asymmetric Shock Resilience, and Inter-Sovereign Trade Tensor Clearing | Regional Network Protocol | ARI-VPE-SIM-2026-01. 156wk, 10 named NSW shires; 6,000 citizens, 100 enterprises, 40,000 ha; 70wk drought at 85% yield collapse; diesel $2.25/L; debt $180.0M to $148.92M; 340 transfers, 3,708.2 t grain; bread invariant $1.15. NEWLY REGISTERED 2026-08-28. | Complete / Simulation Treatise | Not synchronized | https://docs.google.com/document/d/1IjTn4YmNNe9UcNJrMUS2rvibvSp7RN0S-ryac-3T5Bs/edit
VPE-25 | Research Report: Micro-Economy Agent-Based Simulation - Fair-Pricing Protocol vs. Extractive Duopoly Equilibrium | Agent-Based Simulation | 100-timestep 8-stage bread-chain ABM: 300bps rate hike, 100% fuel spike, 40% drought. Milestone M2.1 deliverable. NEWLY REGISTERED 2026-08-28. | Complete / Modeled | Not synchronized | https://docs.google.com/document/d/12RnQibQg49hjBrTFcSJ6OmEi9BWJHFUBPBCfUsyBtV4/edit
VPE-26 | [ARCHIVED] Research Candidate: Formalization of the UPE & P^7 (draft A) | Superseded Draft | Early UPE / 7-Plane Price Vector formalization. Consolidated into VPE-01 per LOG-VPE-013. | Archived / Superseded by VPE-01 | Excluded (archived) | https://docs.google.com/document/d/1pGj5BxMT73HHtjdotLP5DwjZ-Rm7BopIlPqNhG0vmig/edit
VPE-27 | [ARCHIVED] Research Candidate: Formalization of the UPE & P^7 (draft B) | Superseded Draft | Second candidate draft carrying an identical title to VPE-26. Consolidated into VPE-01. | Archived / Superseded by VPE-01 | Excluded (archived) | https://docs.google.com/document/d/1WCe0l00s_4MRwd4VK38oDERYjoJrCdcL2Dq3CJ6_rlM/edit
VPE-28 | [ARCHIVED] UPE_additions.md | Superseded Working Note | Exploratory additions note. Consolidated into VPE-01 per PM Master Log section 3. | Archived / Superseded by VPE-01 | Excluded (archived) | https://docs.google.com/document/d/16jOE-KeF9ykOW8TfEf4NXtsrXnISJostnWu0HODaH-Y/edit
VPE-29 | [ARCHIVED COPY] Value Physics Registry (Aug 24) | Superseded Registry Snapshot | Point-in-time registry snapshot retained for provenance. | Archived | Excluded (archived) | https://docs.google.com/spreadsheets/d/1VdAhjaSazEFKZNSDH1LwujWRw8G_FHeuyepr6CXlVw4/edit
VPE-30 | [ARCHIVED COPY] Value Physics Registry (Aug 24 v2) | Superseded Registry Snapshot | Point-in-time registry snapshot retained for provenance. | Archived | Excluded (archived) | https://docs.google.com/spreadsheets/d/1dq1WC2D-1jioe2SAOIWxfoJ9c2eZD1b4HDvW_650UfI/edit
VPE-31 | [ARCHIVED COPY] Value Physics Master Excel Ledger (superseded 2026-08-28) | Superseded Control Document | Prior ledger. 56-cell tab contradicted FP6 (4 electricity / 2 water stages); LOG-VPE-023 and AUD-VPE-009 missing; LOG-VPE-024 column shift; Leontief source column offset. | Archived / Superseded by VPE-15 | Excluded (archived) | https://docs.google.com/spreadsheets/d/1_rUffeSE_BKVpHiOyicprWGXV-gC8GRZsK7POWSjb0Q/edit
VPE-32 | [ARCHIVED COPY] Project Management Master Log (superseded 2026-08-28) | Superseded Control Document | Prior PM log. Section 1.1 duplicated with copies disagreeing on entry 22; corrupted table fragment; numbering jumped 7 to 16. | Archived / Superseded by VPE-23 | Excluded (archived) | https://docs.google.com/document/d/1KIO1zj-3c-Q_xOPBP_U3KQr3MhFqHG4pxUrqJHGv_RQ/edit
NOTE 2026-08-28: NotebookLM sync has never been verified. Prior revisions reported 15, 20 and 23 sources in three places. Pre-existing rows are marked unverified pending manual reconciliation (OPEN-05).
NOTE: VPE-12, 13, 16 and 17 sit in adjacent institutional directories; all other registered items are in the primary directory.
===== WORKSHEET 2: Formal Change Log =====
Value Physics Research Repository - Master Formal Change Log
Historical progression, formal revisions, adversarial audits, and milestone completions ¦ Revision 2026-08-28
Log ID | UTC Timestamp | Local AEST Time | Operation Category | Target Document / Artifact | Role / Lead | Scope of Changes & Architectural Impact
LOG-VPE-001 | 2026-08-18 02:41 | 2026-08-18 12:41 | Authoring & Proposal | UPE Candidate Draft (VPE-27) | Researcher | Drafted initial formalization of the Universal Price Equation and 7-Plane Price Vector.
LOG-VPE-002 | 2026-08-18 16:57 | 2026-08-19 02:57 | Empirical Research | The Economics and Value Physics of Bread (VPE-10) | Researcher | Audited Australian bread retail pricing across 4 tiers and modeled 5-channel interest rate cost-push dynamics.
LOG-VPE-003 | 2026-08-19 23:01 | 2026-08-20 09:01 | Simulation Modeling | Micro-Economy ABM Bread Simulation (VPE-25) | Researcher | Built 100-timestep 8-stage agent-based simulation evaluating 300 bps rate hikes, 100% fuel spike and 40% drought.
LOG-VPE-004 | 2026-08-20 03:42 | 2026-08-20 13:42 | Treatise Authoring | Cohesive Village Simulation Treatise (VPE-11) | Researcher | Formalized meso-scale 600-citizen village across 7 guilds, Book 1/2/3 Tri-Fold Ledger, and 104-week audit.
LOG-VPE-005 | 2026-08-20 04:00 | 2026-08-20 14:00 | Foundational Formalism | The Cardinal Value Matrix (VPE-05) | Researcher | Mapped WEST, EAST, BEST, WORST 4-quadrant geometry, Need/Want dynamics, and Reciprocal Closure.
LOG-VPE-006 | 2026-08-20 04:35 | 2026-08-20 14:35 | Theoretical Integration | The Grand Translation Treatise (VPE-07) | Researcher | Derived translation equations bridging Value Physics to Neoclassical, Sraffian, Bioeconomic and SFC paradigms.
LOG-VPE-007 | 2026-08-20 16:29 | 2026-08-21 02:29 | Currency Formalization | 7-Plane Token Spectrum Architecture (VPE-06) | Researcher | Constructed multi-spectral currency vector (T), planar action profiles, and eliminated Plane Misidentification Errors.
LOG-VPE-008 | 2026-08-20 16:54 | 2026-08-21 02:54 | Isomorphic Treatise | The Bread of Life Treatise (VPE-08) | Researcher | Mapped 8-stage bread production to Information Theory, Actualism, and the TS_0 reference invariant.
LOG-VPE-009 | 2026-08-20 16:54 | 2026-08-21 02:54 | Master PM Logging | Value Physics Master PM Log (VPE-23) | Project Manager | Initialized master deliverables registry, gap analysis, and open research vectors.
LOG-VPE-010 | 2026-08-20 23:35 | 2026-08-21 09:35 | Simulation Expansion | Multi-Commodity Village Simulation (VPE-04) | Researcher | Extended village model into 5 closed-loop sectors (Food, Energy, Water, Shelter, Care) across 156 weekly timesteps.
LOG-VPE-011 | 2026-08-21 05:12 | 2026-08-21 15:12 | Econometric Calibration | Stock-Flow Consistent (SFC) Model (VPE-03) | Researcher | Calibrated 156-week dynamic SFC agricultural model against ABARES, ABS, RBA, ACCC and AEMO datasets.
LOG-VPE-012 | 2026-08-21 23:52 | 2026-08-22 09:52 | Protocol Specification | Tri-Fold Cryptographic Ledger Whitepaper (VPE-02) | Researcher | Authored mathematical specification of Proof-of-Difficulty consensus and 1,000-run Monte Carlo stress testing.
LOG-VPE-013 | 2026-08-22 08:41 | 2026-08-22 18:41 | Master Consolidation | Formal Paper 6 (VPE-01) | Researcher | Consolidated UPE additions, bread economics, and the Grand Translation into a unified master treatise.
LOG-VPE-014 | 2026-08-22 19:07 | 2026-08-23 05:07 | Epistemic Adversarial Audit | Formal Paper 6 Epistemic Audit (VPE-01) | Checker | Audited Formal Paper 6; flagged formula inversion in the Reality Tensor and a Table 5.1 normalization error. Issued 5 directives.
LOG-VPE-015 | 2026-08-22 22:16 | 2026-08-23 08:16 | Revision & Remediation | Formal Paper 6 Remediation (VPE-01) | Researcher | Remediated the Reality Tensor formula, recalibrated Table 5.1 DQ values to the $5.00 total, added 1inf_U regularization, and defined the M7 gradient.
LOG-VPE-016 | 2026-08-22 22:48 | 2026-08-23 08:48 | Multi-Sector Extension | Formal Paper 6 Energy & Water Additions (VPE-01) | Researcher | Integrated 56-cell reference calibration matrices for Microgrid Energy (1 kWh) and Potable Water (1 kL), plus Section 6.2 Debt Bifurcation.
LOG-VPE-017 | 2026-08-23 03:34 | 2026-08-23 13:34 | Literature Grounding | Orthodox Linker Treatise (VPE-16) | Researcher | Mapped Value Physics to Sraffian Standard Commodities, Godley-Lavoie SFC macroeconomics, and Landauer limits.
LOG-VPE-018 | 2026-08-23 09:12 | 2026-08-23 19:12 | Macro Synthesis | PREF Companion Treatise (VPE-17) | Researcher | Embedded Value Physics (UPE, WEST, P_H, DQ) into the Paradise Reciprocity Economic Framework v5.0.
LOG-VPE-019 | 2026-08-23 17:41 | 2026-08-24 03:41 | Knowledge Base Sync | NotebookLM Sync (3623093f-ad75-41d5-b6e4-5be25ffd8430) | Project Manager | Synchronized 15 master papers into NotebookLM. NOTE: later reported as 20 and 23 elsewhere; unreconciled (OPEN-05).
LOG-VPE-020 | 2026-08-24 05:05 | 2026-08-24 15:05 | Ledger & PM Maintenance | Master Excel Ledger (VPE-15) & PM Master Log (VPE-23) | Project Manager | Established the dedicated master Excel ledger and updated the PM Master Log with the multi-sector roadmap.
LOG-VPE-021 | 2026-08-24 21:44 | 2026-08-25 07:44 | Authoring & Governance | Statutory Model Charter & Sovereign Credit Union Bylaws (VPE-18) | Researcher | Authored complete statutory charter (ARI-VPE-STAT-2026-01) operationalizing Theorem 5 and the Tri-Fold Ledger for regional shires.
LOG-VPE-022 | 2026-08-24 21:44 | 2026-08-25 07:44 | Authoring & Policy | Executive Policy Brief (VPE-19) | Researcher | Authored formal submission (ARI-VPE-POL-2026-01) for Parliamentary/ACCC inquiries modeling rate hike cost-push inflation and duopoly caps.
LOG-VPE-023 | 2026-08-25 12:55 | 2026-08-25 22:55 | Educational Authoring | Value Physics Explained: A Plain-English Beginner's Guide (VPE-20) | Researcher | Authored public-facing primer on UPE, 3-layer cost cake, WEST tokens, DQ, Cohesive Village. RESTORED 2026-08-28: absent from the prior ledger, its description displaced into LOG-VPE-024.
LOG-VPE-024 | 2026-08-26 08:11 | 2026-08-26 18:11 | Journal Authoring | Academic Journal Paper ARI-VPE-JRNL-2026-01 (VPE-21) | Researcher | Authored peer-review manuscript for Ecological Economics / JEDC. CORRECTED 2026-08-28: columns were shifted, putting scope text in the target field and the primer description in the scope field.
LOG-VPE-025 | 2026-08-26 21:40 | 2026-08-27 07:40 | Simulation Scaling | Multi-Village Regional Network Simulation ARI-VPE-SIM-2026-01 (VPE-24) | Researcher | Authored 10-node spatial network simulation treatise across 10 named regional NSW shires under a 70-week drought.
LOG-VPE-026 | 2026-08-27 21:56 | 2026-08-28 07:56 | Simulation Scaling & PM Signoff | Multi-Village Regional Network Simulation ARI-VPE-SIM-2026-02 (VPE-22); Journal manuscript sign-off (VPE-21) | Researcher & PM | Authored the second 10-node treatise (Warrumbungle-Orana) and ran the Sign-Off Protocol audit. CORRECTED 2026-08-28: prior entry attributed this timestamp solely to journal authoring; Drive metadata shows SIM-2026-02 was created then.
LOG-VPE-027 | 2026-08-28 02:00 | 2026-08-28 12:00 | Control Document Reconciliation | Master Excel Ledger (VPE-15) & PM Master Log (VPE-23) | Project Manager | Rebuilt both control documents: replaced the drifted 56-cell tab with a verification record pointing to FP6; restored LOG-VPE-023 and AUD-VPE-009; fixed LOG-VPE-024 column shift and Leontief source offset; registered 7 unlisted files (VPE-24 to VPE-30); archived superseded controls (VPE-31, VPE-32); corrected AUD-VPE-010 shock parameters and M4.5 status; added M5.4 and M5.6; introduced evidence tiers and the open items register.
===== WORKSHEET 3: 56-Cell Verification =====
Value Physics 56-Cell Empirical Calibration - Verification Record
Sector totals, integrated Leontief embodied difficulty, and the independent verification record ¦ Revision 2026-08-28
Sector Standard | Stages | Total WEST | Total AUD | Primary Production DQ | Retail / Financial Toll DQ | Official Benchmark Source | Calibration Status
Bread (TS_0 - 700g Loaf) | 8 | 4.69 W | 5 | 0.26 (stages 1-3 grain) | 10.66 (stage 8 retail) | ABARES / NSW DPI / ACCC Supermarket Inquiry | Complete / Verified
Electricity (1 kWh Microgrid) | 8 | 2.05 W | 0.285 | 0.24 (stage 1 PV) | 15.11 (stage 8 gentailer) | AEMO QED / Clean Energy Council / ARENA / AER | Complete / Verified
Water (1 kL Potable) | 8 | 2.80 W | 3 | 0.23 (stage 1 catchment) | 13.69 (stage 8 utility levy) | NSW Water Utility Benchmarks / WSAA / NSW DPI | Complete / Verified
Shelter (1 Unit / Week) | 8 | 5.40 W | 65 | 0.31 (stage 4 rammed earth) | 18.28 (stage 8 mortgage) | Master Builders Australia / CSIRO Housing | Complete / Verified
Care (1 Unit Clinical) | 8 | 3.20 W | 45 | 0.36 (stage 4 clinical) | 20.62 (stage 8 insurance) | AIHW National Health & Care Metrics | Complete / Verified
INTEGRATED LEONTIEF EMBODIED DIFFICULTY | d_integrated = d_direct x (I - A)^-1 | Direct (W) | Integrated (W) | Indirect uplift |  | Official Benchmark Source | Calibration Status
Food (Bread TS_0) |  | 0.5474 | 0.565 | +3.2% |  | ABARES Cropping Farm Survey (NSW) | Verified - recomputed 2026-08-28
Energy (1 kWh) |  | 0.1025 | 0.1092 | +6.5% |  | AEMO Quarterly Energy Dynamics (QED) | Verified - recomputed 2026-08-28
Water (1 kL) |  | 0.14 | 0.1961 | +40.1% |  | NSW DPI Irrigation Energy Audits | Verified - recomputed 2026-08-28
Shelter (1 Week) |  | 5.4 | 7.5816 | +40.4% |  | Master Builders Australia / CSIRO Housing | Verified - recomputed 2026-08-28
Care (1 Unit) |  | 1.75 | 2.0989 | +19.9% |  | AIHW National Health & Care Metrics | Verified - recomputed 2026-08-28
ARCHITECTURAL CHANGE 2026-08-28: the full 56-cell per-stage matrices are published in Formal Paper 6 sections 5.1-5.5 and are NO LONGER DUPLICATED here. Duplicating them is what produced the prior defect - this tab had drifted to 4 Electricity stages and 2 Water stages with per-stage WEST, AUD and DQ values that did not match Formal Paper 6. Formal Paper 6 is the single source for per-stage calibration; this worksheet carries only sector totals, the integrated vector, and the verification record.
VERIFICATION 2026-08-28: all five sectors re-derived independently from Formal Paper 6. Every WEST and AUD column sums to its stated sector total, and all 40 DQ values reproduce from (AUD share)/(WEST share) within rounding. The published (I-A)^-1 was re-derived from FP6's technical-coefficient matrix A (max deviation 4.9e-05); spectral radius of A is 0.129, so the system is productive. d_direct x (I-A)^-1 reproduces [0.5650, 0.1092, 0.1961, 7.5816, 2.0989].
CORRECTION 2026-08-28: the Leontief block's benchmark-source column was previously offset by one row (Master Builders/CSIRO against Food, AIHW against Energy). Sources are now aligned to their own sectors.
OPEN-02 (UNRESOLVED): the sector totals and the d_direct Leontief inputs are NOT on a common unit. Ratios: Food 8.57x, Energy 20.00x, Water 20.00x, Shelter 1.00x, Care 1.83x. Only Food is documented (FP6 5.1, batch vs single loaf). Until reconciled, d_integrated must not be compared against the sector WEST totals.
===== WORKSHEET 4: Audits & Directives Tracker =====
Value Physics Epistemic Audits & Corrective Directives Tracker
Adversarial review log, checker feedback, structural directives, evidence tier, and resolution signoffs ¦ Revision 2026-08-28
Audit ID | Target Document | Auditor Role | Audit Date | Identified Vulnerability / Discrepancy | Corrective Directive Issued | Resolution Status | Evidence Tier | Verification Evidence
AUD-VPE-001 | Formal Paper 6 (2.3 & 3.1) | The Checker | 2026-08-22 | Critical algebraic inversion in the Universal Price Equation: the Reality Tensor was inverted as Rn(1-Ra)/(S*U). | Invert to canonical form (S*U)/[Rn(1-Ra)] across scalar and 7-plane forms. | CLOSED | E2 - Recomputed | Corrected in Formal Paper 6 sections 2.3 and 3.1; canonical form confirmed present.
AUD-VPE-002 | Formal Paper 6 (Table 5.1) | The Checker | 2026-08-22 | Arithmetic normalization error: nominal AUD costs summed to $5.00 but the reported DQ used a $7.50 total. | Recalibrate Table 5.1 DQ values to strictly match the $5.00 total (DQ_Distrib = 10.66). | CLOSED | E2 - Recomputed | Table 5.1 recalibrated. Independently re-derived 2026-08-28: WEST column sums to 4.69 W, AUD to $5.00, and all 8 DQ values reproduce exactly.
AUD-VPE-003 | Formal Paper 6 (3.2) | The Checker | 2026-08-22 | Zero-division singularity in relative urgency velocity when U_A = U_B = 0. | Regularize v_rel with the Cost of Being boundary floor: v_rel = ¦UA - UB¦ / [max(UA,UB) + 1inf_U]. | CLOSED | E1 - Textual | Regularization present in Formal Paper 6 section 3.2.
AUD-VPE-004 | Formal Paper 6 (3.3) | The Checker | 2026-08-22 | Domain ambiguity in the directional value gradient operator V = -grad P. | Define the M7 gradient as the exterior derivative on the Riemannian 7-Plane Price bundle. | CLOSED | E1 - Textual | Exterior derivative formalized in section 3.3.
AUD-VPE-005 | Formal Paper 6 (6.3) | The Checker | 2026-08-22 | Placeholder metadata in the verification block. | Populate formal author, auditor, institution, date and location metadata. | CLOSED | E1 - Textual | Metadata block populated. NOTE: populated with agent role names, not named human authors - see OPEN-04.
AUD-VPE-006 | SFC Econometric Paper (VPE-03) | The Checker | 2026-08-23 | Verify 5-year balance sheet stock-flow closure under extreme stochastic interest rates. | Execute extended 260-week stress simulation to guarantee zero financial leakages. | PARTIAL (Godley-Lavoie transaction matrix verified in text; code replication package OPEN-01 active) | E1 - Textual (claims E3) | Reported 156/156 and 260/260 passes, zero leakages. No code, seeds, logs or outputs retained, so E3 is not met. See OPEN-01.
AUD-VPE-007 | Tri-Fold Ledger Whitepaper (VPE-02) | The Checker | 2026-08-23 | Audit smart contract covenants to ensure r_compound == 0.0% invariant under inflation. | Stress-test Book 1 linear amortization rules under simulated 15% fiat inflation. | CLOSED | E1 - Textual (claims E3) | Reported 1,000/1,000 passes, 0 defaults, 100% solvency. No run artifacts retained. See OPEN-01, OPEN-06.
AUD-VPE-008 | Policy Brief (VPE-19) & Model Bylaws (VPE-18) | Epistemic Auditor | 2026-08-25 | Verify alignment of the Model Credit Union Bylaws with the Australian Corporations Act 2001 (Mutuals). | Audit Articles II and IV against APRA prudential standards and Theorem 5 linear amortization schedules. | CLOSED | E1 - Textual | Cross-verified vs Corporations Act 2001 Pt 5C and RIC Act 2018. Art II s2.02 mandates r_compound = 0%; Art IV s4.02 caps Ra <= 0.12.
AUD-VPE-009 | Formal Paper 6 (5.6) & Journal Manuscript (VPE-21, 3.2) | Engineer | 2026-08-28 | Validate the 5-sector Leontief-Value Tensor inversion and integrated difficulty vector against indirect thermodynamic and labor multipliers. | Verify (I - A)^-1 inversion and d_integrated across all 5 sub-sectors. | CLOSED | E2 - Recomputed | RESTORED 2026-08-28 (was in the PM log, missing here). Verified: published inverse matches a fresh inversion of A to 4.9e-05, spectral radius 0.129, d_direct x (I-A)^-1 reproduces [0.5650, 0.1092, 0.1961, 7.5816, 2.0989]. 5/5 PASS.
AUD-VPE-010 | Multi-Village Simulation ARI-VPE-SIM-2026-02 (VPE-22) | Engineer | 2026-08-28 | Verify dynamic stability of the 10-node Regional Trade Tensor and Leontief inverse under localized drought. | Validate 0/10 node defaults and linear debt amortization. | CLOSED | E1 - Textual (claims E3) | CORRECTED 2026-08-28: prior entry cited a 70-week drought (a SIM-2026-01 parameter) against SIM-2026-02 results. Correct shock is a 30-week localized drought (wks 40-70) at 50% yield loss. Results (0/10 defaults, debt to $147.04M, 42.0M WEST reserves) are correct for SIM-2026-02. No run artifacts retained.
AUD-VPE-011 | Formal Paper 6 (5) & Journal Manuscript (VPE-21, 3.1-3.2) | External Review | 2026-08-28 | The 56-cell sector WEST totals and the d_direct Leontief inputs use inconsistent per-sector scale factors: Food 8.57x, Energy 20.00x, Water 20.00x, Shelter 1.00x, Care 1.83x. Only the Food case is documented. | Publish a per-sector unit-conversion note generalizing the FP6 5.1 bread clarification; derive the Care 1.83x factor from source. | PARTIAL (Food batch documented; Energy/Water/Care PIOT concordance appendix active) | E2 - Recomputed | Ratios computed from values published in FP6 5.1-5.6 and JRNL 3.1-3.2. Tracked as OPEN-02.
AUD-VPE-012 | ARI-VPE-SIM-2026-01 (VPE-24) & ARI-VPE-SIM-2026-02 (VPE-22) | External Review | 2026-08-28 | Two distinct 10-node simulations with incompatible parameterizations were tracked under a single registry slot; the two copies of the PM Master Log registry disagreed on which document that slot referred to. | Register both treatises separately and correct the AUD-VPE-010 shock parameters. | CLOSED | E2 - Recomputed | Rows VPE-22 and VPE-24 now carry the two treatises separately. AUD-VPE-010 corrected above.
AUD-VPE-013 | Master Excel Ledger (VPE-15) & PM Master Log (VPE-23) | External Review | 2026-08-28 | Control document integrity: 56-cell tab contradicted FP6 on Electricity and Water; LOG-VPE-023 and AUD-VPE-009 missing; LOG-VPE-024 column shift; Leontief source column offset; 7 folder files unregistered; roadmap M5.4 absent; M4.5 status conflicted; NotebookLM count reported as 15, 20 and 23. | Rebuild both control documents and archive the superseded revisions. | CLOSED | E2 - Recomputed | This revision. Superseded originals retained as VPE-31 and VPE-32.
AUD-VPE-014 | ARI-VPE-SIM-2026-01 (VPE-24) | The Checker | 2026-08-28 | Markdown formula remediation | Remediate markdown formulas | CLOSED (Remediated equation formatting in SIM-2026-01) | E1 - Textual | Verified evidence
OPEN-01 |  |  |  | code replication package |  | OPEN
OPEN-02 |  |  |  | Unit reconciliation |  | OPEN
OPEN-03 |  |  |  | Theorem 2.1 grounding |  | OPEN
OPEN-04 |  |  |  | named authorship/ORCIDs |  | OPEN
OPEN-05 |  |  |  | NotebookLM sync reconciliation |  | OPEN
OPEN-06 |  |  |  | dispersion |  | OPEN
OPEN-07 |  |  |  | precision rounding |  | OPEN
EVIDENCE TIERS (2026-08-28). E1 Textual: claim re-read in the target document - editorial/metadata directives only. E2 Recomputed: figure independently re-derived from published inputs - arithmetic and algebraic directives. E3 Executed: code run with artifacts (version, seed, logs, output) retained - required for any simulation or Monte Carlo claim.
STANDING GAP: AUD-VPE-006, 007 and 010 assert executed results but no code, seeds, logs or outputs exist. Marked 'evidence downgraded'; not citable as reproducible evidence until M5.5 delivers the replication package.
===== WORKSHEET 5: Strategic Roadmap =====
Value Physics Strategic Research Roadmap
The 5-phase trajectory toward a validated replacement macroeconomic model ¦ Revision 2026-08-28
Phase # | Phase Name | Milestone / Work Package | Technical & Empirical Deliverable | Target Horizon | Status | Key Lead / Responsible
Phase 1 | Foundational Theory | M1.1: Universal Price Equation Formalization | UPE scalar and field equations, 3-layer cost decomposition, 7-Plane Price Vector | Historical | COMPLETED | Researcher
Phase 1 | Foundational Theory | M1.2: Canonical TS_0 Reference Standard | 8-stage bread lifecycle mapped to Information Theory, Actualism, and the physical invariant floor | Historical | COMPLETED | Researcher
Phase 2 | Micro-Economy Modeling | M2.1: 8-Stage Agent-Based Simulation | 100-timestep supply chain simulation evaluating RBA rate hikes and retail duopoly markups (VPE-25) | Historical | COMPLETED | Researcher
Phase 2 | Micro-Economy Modeling | M2.2: Stock-Flow Consistent Macro Model | 156-week empirical econometric model calibrated against ABARES/RBA/ACCC datasets | Historical | COMPLETED | Researcher
Phase 3 | Meso-Scale & Protocol | M3.1: 5-Sector Closed-Loop Village Simulation | Coupled Food, Energy, Water, Shelter, Care simulation across 156 weeks under compound shocks | Historical | COMPLETED | Researcher
Phase 3 | Meso-Scale & Protocol | M3.2: Tri-Fold Cryptographic Ledger Whitepaper | PoD consensus specification and 1,000-run Monte Carlo testing (documented, not reproducible - OPEN-01) | Historical | COMPLETED | Researcher
Phase 4 | Multi-Sector Standards | M4.1: Formal Paper 6 Remediation & Polish | Checker directives resolved, Reality Tensor verified, Table 5.1 recalibrated, metadata signed | Completed | COMPLETED | Researcher / Checker
Phase 4 | Multi-Sector Standards | M4.2: Energy (kWh) & Water (kL) Matrices | Empirical 56-cell matrices for solar/hydro microgrids and potable water catchment, at full 8 stages | Completed | COMPLETED | Researcher
Phase 4 | Multi-Sector Standards | M4.3: Educational Primer Authoring | Plain-English Beginner's Guide for public onboarding and policy translation (VPE-20) | Completed | COMPLETED | Researcher
Phase 4 | Multi-Sector Standards | M4.4: Shelter & Care 56-Cell Calibration | Formal 56-cell matrices for modular rammed-earth construction and clinical/educational labor | Completed | COMPLETED | Researcher
Phase 4 | Multi-Sector Standards | M4.5: Automated Evaluation Scripts & Tooling | Python/Rust CLI tools for automated 56-cell DQ calculation and PoD block header validation | Sprint Active | ACTIVE | Engineer
Phase 4 | Multi-Sector Standards | M4.6: Continuous NotebookLM Knowledge Base Sync | Maintain sync into notebook 3623093f-ad75; source count requires reconciliation (OPEN-05) | Ongoing | ACTIVE | Project Manager
Phase 5 | Replacement Macro Model | M5.1: Academic Journal Paper Submission Suite | Consolidated manuscript ARI-VPE-JRNL-2026-01 for Ecological Economics / JEDC | Completed | COMPLETED | Triad Team
Phase 5 | Replacement Macro Model | M5.2: Regional Banking & Credit Union Charter | Statutory model charter and bylaws for Theorem 5 debt bifurcation (ARI-VPE-STAT-2026-01) | Completed | COMPLETED | Researcher / PM
Phase 5 | Replacement Macro Model | M5.3: Sovereign Policy Briefing for Inquiries | Executive policy brief for Senate/ACCC regulatory inquiries (ARI-VPE-POL-2026-01) | Completed | COMPLETED | Directorate / PM
Phase 5 | Replacement Macro Model | M5.4: 10-Node Regional Network Simulation Treatises | ARI-VPE-SIM-2026-01 (VPE-24) and -02 (VPE-22). ADDED 2026-08-28: absent from the prior ledger roadmap. | Completed | COMPLETED | Researcher
Phase 5 | Replacement Macro Model | M5.5: Open-Source Repository & Web Dashboard | Package the simulation and SFC replication scripts with pytest suites, pinned seeds and retained run logs (OPEN-01) | Sprint Active | ACTIVE | Engineer
Phase 5 | Replacement Macro Model | M5.6: Submission-Readiness Package | Unit reconciliation (OPEN-02), Theorem 2.1 grounding (OPEN-03), named authorship/ORCIDs (OPEN-04), dispersion (OPEN-06), precision rounding (OPEN-07). ADDED 2026-08-28. | Sprint Active | ACTIVE | Triad Team
CORRECTION 2026-08-28: M4.5 was COMPLETED in the PM log and ACTIVE in the ledger; no scripts exist, so ACTIVE is accurate. Shelter & Care calibration, previously ACTIVE, is COMPLETED - both matrices are published in FP6 5.4-5.5.